## Ark1
Wind vessels for the future |  |  |  | OEM = Original Equipment Manufacturer |  | H = Harbours
Sub-speed boat |  |  |  | SO = Ship Owners |  | TC = Transport Companies
Meeting on October 12, 2020 |  |  |  | C = Contractors |  | FO = Farm Owners
Dimensions to consider
|  | Themes identified | What is the challenge? | Wherein lies the value creation? | For whom is the value created? | How is the project executed? | What do we need to do? | How much time is required? | Can we resolve it in this team complexity wise? | How much money will it cost?
| 1 | Understand dimensions/weights of 20 MW and 25 MW wind turbines (synchronize with existing and future ports sub-speed boat). This information is a pre-requisite for the other themes… | Uncertainty and availability of data, to what degree can components be splitted | Forms the basis for design of vessels and equipment (which has a lead time) | ALL | OEM's are the key provider of information | Gain firm knowledge on dimensions of components, ability to split components, projected number of turbines incl location | Months perhaps | Reaching limit for what the market can handle given the large volume of offshore wind farm projects and number of wind turbines in a single project (e.g. 800 MW project 32x 25 MW wind turbines, more tower sections, many restrictions, high transport cost). Maybe savings from something different from transport?
| 2 | Number of transport vessels with heavy lift capabilities available compared to transport volumes (supply and demand now and in the future) | Bottleneck and time delay until vessels are designed and built | Less delays on long-haul transport of components, cost reduction, more reliable supply chain | OEM, C, FO, SO | Supply chain analysis, projections of future demands | Define current and predicted future demand for tonnage and approximate size of the components | Decision to do something 1-3 years; vessel design itself takes 6 months; from approved design and agreement with yard the delivery time for the first vessel is 18 (to 24) months with subsequent deliveries every 3 months | Cranes are a major issue for vessels; today only approx. 20 vessels exist worldwide with a total of 1400 T crane capacity on board (and most are old)
| 3 | Feeder barges to installation vessel concept discussions (China, USA, MHI Vestas Offshore Wind) | Jones Act (and similar in Japan), lacks barge-to-jackup transport concepts (weather window restrictions) | Installation in US and japanese waters using foreign vessels. Installation vessel can stay at sea, cost reduction | C, FO, SO | Innovation, pilot projects | Propose technical solutions and rank by costs and effectiveness | A few years | Wind turbine will be discharged at port and then loaded on to feeder barge; feeder barge limited capacity; limited number of feeder barges e.g. in the USA
| 4 | Vessel solutions to cater for blades of 125 meters and above in length (primary focus is installation) | Bigger vessels demands bigger terminals. Terminals able to handle large transport frames (stacked blades) | Alternative is perhaps more costly, use of heavy lift vessels for instance (more optimal vessel types could be devised) | OEM, C, FO | Innovation | Define current and predicted future demand for tonnage and approximate size of the components |  | Blade center of gravity; new installation vessels (1x USA, 1x TW, 3-4x JP, OHT); lack of ship design consultancies
| 5 | Design common interfaces for transport frames to be used across different wind turbine manufacturers across modes, i.e. land transport plus port operations plus on board vessels (is this impossible for us to impact - OEMs will have to drive forward) | To ensure that standard interfaces are usable 5 and 10 years ahead | Reuse of material, cost reduction, save time preparing vessels | ALL (too insecure to add value for SOs) | All relevant partners to agree on standards. This is often time consuming and there is a risk standards will be ready too late (due to ever rising sizes of turbines). | Involve OEMs' if possible… | Years | Frames are very expensive for OEMs to make; the use of frames should be from point of manufacture and as far through the logistics chain as possible; OEMs do not agree on whether to stack the blades or not (MHI Vestas/GE-LM stack blades, SGRE does not)
| 6 | Installation and O&M of floating offshore wind turbines | Number of concepts needs to be boiled down and we believe approx. 50 concepts exist and that 5 will survive. Floating offshore not yet matured | Optimized concepts, less steel, quicker assembly, standardised anchoring systems => lower LCOE | ALL | We could add value along critical dimensions (crane reach for 3-point foundations; port depth; lifting height 130-150 meters; lack of available land cranes as well as time/cost to mobilize those that exist; inavailability of floating cranes able to match lifting height/weight requirements; floating to floating lift concepts for O&M still developing (alternative is to tow back to port). Innovation, pilot projects | The next 3-5 years we are probably still in "pilot projects" phase? |  | 1-2 tugs; cheap. Stiesdal, Equinor, Maersk… | SGRE and MHI Vestas are the leading OEMs and the Danish supply chain can therefore choose to support in key areas like France, Portugal, Scotland, Japan, and the US. However, the associated risks need to be visualized as companies would need to be able to "pick a winner" and be acutely aware of the risk involved